## Ark 1
Project - Lofthus frukt & saft
| PLAN | [47 empty] | DESIGN | [47 empty] | BUILD | [39 empty] | LAUNCH
| Day 1 | [7 empty] | Day 2 | [7 empty] | Day 3 | [7 empty] | Day 4 | [7 empty] | Day 5 | [7 empty] | Day 6 | [7 empty] | Day 5 | [7 empty] | Day 7 | [7 empty] | Day 8 | [7 empty] | Day 9 | [7 empty] | Day 10 | [7 empty] | Day 11 | [7 empty] | Day 12 | [7 empty] | Day 13 | [7 empty] | Day 14 | [7 empty] | Day 15 | [7 empty] | Day 16 | [7 empty] | Day 17 | [7 empty] | Day 18 | [7 empty] | Day 19 | [7 empty] | Day 20 | [8 empty] | Day 21
PROJECT MANAGER ONGOING CUSTOMER CONTACT
PROJECT MANAGER KICK-OFF MEETING | 1
PROJECT MANAGER PROJECT PLANNING |  | 1 | 1 | 1 | 1 | 1 | 1 | 1
PROJECT MANAGER MEETING: agreeing on plan/order/deliverytime | [8 empty] | 1
DEVELOPER and DESIGNER RESEARCH: competition, market, product and target group | [8 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
PROJECT MANAGER, DEVELOPER AND DESIGNER STRATEGI PLANNING | [20 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
CONTENT DEVELOPER, DESIGNER and DEVELOPER SITE OUTLINE | [40 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
CONTENT DEVELOPER, DESIGNER and DEVELOPER SITE STRUCTURE | [48 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
DESIGNER CREATE STYLETILE and IDENTITY ELEMENTS | [63 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
PHOTOGRAPHER PHOTOSHOT: Identity, production, product, location, employ.. | [72 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
DEVELOPER CODING, INTEGRATION and SITE BUILD | [95 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
DEVELOPER CROSS PLATFORM and BROWSER TESTING | [144 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
DEVELOPER VALIDATING | [152 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
CONTENT DEVELOPER, DESIGNER and DEVELOPER REFINEMENT | [160 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
PROJECT M, CONTENT DEV, DESIGNER and DEVELOPER LAUNCH | [168 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
CONTENT DEVELOPER CONTENT PLANNING | [40 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
CONTENT DEVELOPER CONTENT DEVELOPMENT | [64 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
DEVELOPER GETTING DOMAIN AND WEBHOST | [15 empty] | 1 | 1
PROJECT MANAGER SETTING UP COLABORATION ENVIRONMENT | [6 empty] | 1 | 1
PROJECT MANAGER BOOK PHOTOGRAPHER | [66 empty] | 1 | 1
DESIGNER WIREFRAMES | [95 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
DEVELOPER WAG-TESTING | [127 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
DEVELOPER, CONTENT DEVELOPER, DESIGNER UI/UX PLANING and TESTING | [106 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
DEVELOPER, CONTENT DEVELOPER, DESIGNER UI/UX TESTING | [135 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1